## Daily Inspection Report
DAILY INSPECTION REPORT
PROJECT DESCRIPTION AND LOCATION |  |  | CONTRACT No. | [5 empty] | WEATHER |  |  |  | PREPARED BY
|  |  | PROJECT ID | [5 empty] | AM
|  |  | CONTRACTOR | [5 empty] | PM |  |  |  | DATE | 2015-06-23
Project Start Date |  | Working Day No. |  |  |  | Report No. |  |  |  |  | Rev. No. |  | Picture Qty
Inspector On-Site |  | Inspector Off-Site |  |  |  | Contractor On-Site | [5 empty] | Contractor Off-Site
RESOURCES ON SITE
Labour
Duty (Name) |  |  | Crew No. and Type |  |  |  |  | Hours |  | Company
Supervisor
Foreman
Labourer
Operator
Equipment
Type (Model) | [7 empty] | Hours |  | Company
Materials
Type |  |  | Qty |  |  | Delivered / Used |  |  |  | Approved Shop Drawing
HEALTH AND SAFETY
Incidents / Safety Meetings
1.
Observations* | [14 empty] | *If a safety infraction is observed, complete form "Construction Services - Notice of Safety Infraction".
1.
ENVIRONMENTAL
Incidents / ESC Measures
1.
Observations
1.
PROGRESS OF WORK |  |  |  |  | ACTION
|  |  |  | Yes: | None.
|  |  |  | No: | Coordinate with contractor to field verify applicable items.
|  |  |  | Yes: | None.
|  |  |  | No: | Update as-built records as per recent progress of work.
Observations
1.
SCHEDULE UPDATE |  |  |  |  | ACTION | [9 empty] | Total Weather Days (to date): 0
|  |  |  | Yes: | Record under observations. Notify project team.
|  |  |  | No: | None.
|  |  |  | Yes: | None.
|  |  |  | No: | Record under observations. Discuss with contractor.
|  |  |  | Yes: | None.
|  |  |  | No: | Record under observations. Discuss with contractor.
Observations
1.
PROTECTION OF PROPERTY / PERMITS AND APPROVALS |  |  |  |  | ACTION
|  |  |  | Yes: | Record under observations. Notify project team.
|  |  |  | No: | None.
|  |  |  | Yes: | Issue site instruction concerning applicable permit or approval.
|  |  |  | No: | None.
|  |  |  | Yes: | None.
|  |  |  | No: | Issue site instruction concerning dewatering.
Observations
1.
SPECIFICATION ITEMS
Item - Specification Section: Description | [7 empty] | Location |  |  |  |  | Photo
1. | [7 empty] | DESCRIPTION AND/OR SKETCH |  |  |  |  | PHOTO
2. | [7 empty] | DESCRIPTION AND/OR SKETCH |  |  |  |  | PHOTO
3. | [7 empty] | DESCRIPTION AND/OR SKETCH |  |  |  |  | PHOTO
Materials Testing | [7 empty] | Performed By |  |  |  |  | Results (Attach)
1.
DISCUSSION ITEMS
1.
VISITORS AND CORRESPONDENCE
1.
PHOTOGRAPHS AND SKETCHES
| Site Inspector (Print) | [5 empty] | Site Inspector (Signature & Date)
Difficulties encountered on site which may impact schedule?
Work generally proceeding in accordance with project schedule?
Are "as-built" records up to date?
Permit or Approval approaching expiry (+/- 1 month)?
Property damage encountered due to work activities?
Dewatering activities proceeding in accordance with PTTW limits?
Has look-ahead work been field verified?
Work proceeding in accordance with contractor look-ahead schedule?